## Sheet1
SELECTED BACKLOG ITEMS | TASKS NOT STARTED | TASKS IN-PROGRESS | TASKS COMPLETED
Attempting to update a ballot that has no remaining candidates causes system failure
As an election official I want the IR election process to run properly So that the system doesn’t fail Acceptance Criteria: System doesn’t fail Definition of Done: Don’t remove a candidate that has no more candidates left to remove Effort: Small |  |  | - Add code to check if no candidates remain. Ashton - Unit testing. Ashton
System fails for CPL elections when more seats are allocated to a party than there are candidates
As an election official I want the CPL election process to run properly So that the system doesn’t fail Acceptance Criteria: System doesn’t fail Definition of Done: Don’t allow more seats to be allocated than they have, Allocate the seat to the party with the next highest remainder Effort: Small |  | - Add a check/conditional to see if a party has all of its seats allocated. GARRETT - Unit testing. GARRETT
Generating audit file alongside of working directory instead of inside of working directory.
As an election official I want the audit file to generate inside the same directory as the program So that I can find and access the file easily Acceptance Criteria: Audit file appears in the same directory as the program Definition of Done: Generate the audit file inside the working directory Effort: Small |  |  | - Discover if this is intended, or a bug. CALEB
Auditing ties in CPL Elections will display the index of the parties in a tie, not the name of the parties.
As an election official I want to view the parties that are in a tie in CPL processing So that I can see who wins the fair coin toss. Acceptance Criteria Correct party names are displayed to the terminal when a tie occurs. Definition of Done String names of the tied parties are displayed instead of their indexes. Effort: Small | - Have the audit file display the names of parties instead of the index | - Correct this index error. ELIAS
Multiple filenames can be entered for processing.
As an election official I want to be able to use CSV files So that they can be processed in any election. Acceptance Criteria: Can select a CSV ballot file to run on any election. Definition of Done: Ability to select desired CSV to be processed, Runs selected election with the files. Effort: Medium | - IR processing can handle multiple files. - CPL processing can handle multiple files. - Unit testing on filenames stored. - New system tests for CPL and IR using multiple CSV files. | - Stores multiple filenames for processing. GARRETT
Result table pop-up for IRV election
As an election official I want a table displayed after processing an IRV election that shows how each round went So that I can see how the election progressed. Acceptance Criteria: A table gets displayed on the screen Each candidate and party is shown in the table The table has information from each round of the election The number of votes each candidate gained or lost in a round is shown Definition of Done: The table contains accurate election information gathered from election processing The table has each candidate and their political party The table has a column for each round The column for each round has how many votes each candidate has at the end of that round The column for each round shows how many votes each candidate gained or lost that round The number of exhausted ballots from each round are in the table Total number of valid ballots are shown in the table Table is displayed to the screen Effort: Medium | - Calculate data to be displayed in the table. - Display a table after IRV election has been processed. - Unit testing. | - Create a data structure for holding table results. CALEB
Use CSV file for PO election processing
As an election official I want to be able to use CSV files So that they can be processed in an PO election. Acceptance Criteria (conditions that have to be fulfilled to ensure the story is complete) Can select a CSV ballot file to run a PO election. Definition of Done (what is required by the team before sending out for review) Ability to select desired CSV to be processed Runs a PO election with the file. Effort: Medium | - Add method to read in CSV files - Unit Testing
Run Popularity Only (PO)
As an election official I want to be able to run a Popularity Only (PO) So that I can determine the winner of a PO election. Acceptance Criteria Have the ability to run a PO election in the software. Definition of Done Implement PO processing Detect and run PO elections from selected files chosen by election officials. Effort: Extra Large | - Implement this in a way multiple files/ballots are used - Unit Testing | - Create class objects that process PO election. Ashton